## Sheet
Future Orders
Account: | Lennar Corporation - Lennar Orange County | Plan: | -- All -- | EPO: | -- All --
Subdvision: | OCH - Arches - 1157451 | Job Address: | -- All -- | Future Days: | 90
Phase: | PRODUCTION/WARRANTY | Builder's Order #: |  | Look Back Days: | -- All Scheduled Tasks --
Group: | PH07 - HS 0044-0049, 0144-0142 (NOV) | Order Type: | -- All --
Account | Subdivision | Phase | Group | Job Start Date | Job | Lot/Block | Plan | Elevation | Swing | Task Start Date | Task | PO Contract Date | Builder's Order # | Order Type | EPO | Tax Amount | Job Subtotal Tax (Excl Tax) | Total
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-01 | 1025900 - Arches0150 - 24000 Camino Oceano 24000 Camino Oceano | 0150/ | 1 | A | UNKWN | 2026-03-02 | Painting - Interior / Prep & Enamel (437214) (INT) [LS] [578700 - 34718289-000] [OP] | 2025-12-02 | 34718289-000 | Purchase Order | No | 0 | 3577.65 | 3577.65
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-01 | 1025900 - Arches0150 - 24000 Camino Oceano 24000 Camino Oceano | 0150/ | 1 | A | UNKWN | 2026-03-07 | Painting - Exterior (437237) (EXT) [578700 - 34755302-000] [UA] | 2025-12-02 | 34755302-000 | EPO | Yes | 0 | 715.89 | 715.89
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-01 | 1025900 - Arches0150 - 24000 Camino Oceano 24000 Camino Oceano | 0150/ | 1 | A | UNKWN | 2026-03-12 | Painting - Exterior (437213) (EXT) [578700 - 34730495-000] [UA] | 2025-12-02 | 34730495-000 | EPO | Yes | 0 | 952.68 | 952.68
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-01 | 1025900 - Arches0150 - 24000 Camino Oceano 24000 Camino Oceano | 0150/ | 1 | A | UNKWN | 2026-03-17 | Painting - Exterior (437235) (EXT) [LS] [578700 - 34726062-000] [OP] | 2025-12-02 | 34726062-000 | Purchase Order | No | 0 | 3506.07 | 3506.07
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-01 | 1025900 - Arches0150 - 24000 Camino Oceano 24000 Camino Oceano | 0150/ | 1 | A | UNKWN | 2026-03-22 | Painting - Exterior / Prep & Enamel (437214) (INT) [LS] [578700 - 34758878-000] [OP] | 2025-12-02 | 34758878-000 | Purchase Order | No | 0 | 3062.43 | 3062.43
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-04 | 1025901 - Arches0151 - 24002 Camino Oceano 24002 Camino Oceano | 0151/ | 1 | B | UNKWN | 2026-03-05 | Painting - Base Shoe (Flooring Orders) (437217) (INT) [LS] [578700 - 34720379-000] [OP] | 2025-12-05 | 34720379-000 | Purchase Order | No | 0 | 1753.6 | 1753.6
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-04 | 1025901 - Arches0151 - 24002 Camino Oceano 24002 Camino Oceano | 0151/ | 1 | B | UNKWN | 2026-03-10 | Painting - Base Shoe (Flooring Orders) (437206) (INT) [LS] [578700 - 34712156-000] [OP] | 2025-12-05 | 34712156-000 | Purchase Order | No | 0 | 2329.75 | 2329.75
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-04 | 1025901 - Arches0151 - 24002 Camino Oceano 24002 Camino Oceano | 0151/ | 1 | B | UNKWN | 2026-03-15 | Painting - Base Shoe (Flooring Orders) (437222) (INT) [LS] [578700 - 34779131-000] [OP] | 2025-12-05 | 34779131-000 | Purchase Order | No | 0 | 1925.82 | 1925.82
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-04 | 1025901 - Arches0151 - 24002 Camino Oceano 24002 Camino Oceano | 0151/ | 1 | B | UNKWN | 2026-03-20 | Painting - Exterior (437246) (EXT) [LS] [578700 - 34760217-000] [OP] | 2025-12-05 | 34760217-000 | Purchase Order | No | 0 | 2876.8 | 2876.8
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-04 | 1025901 - Arches0151 - 24002 Camino Oceano 24002 Camino Oceano | 0151/ | 1 | B | UNKWN | 2026-03-25 | Painting - Exterior / Prep & Enamel (437205) (INT) [LS] [578700 - 34772357-000] [OP] | 2025-12-05 | 34772357-000 | Purchase Order | No | 0 | 2026.12 | 2026.12
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-04 | 1025901 - Arches0151 - 24002 Camino Oceano 24002 Camino Oceano | 0151/ | 1 | B | UNKWN | 2026-03-30 | Painting - Base Shoe (Flooring Orders) (437236) (INT) [LS] [578700 - 34725203-000] [OP] | 2025-12-05 | 34725203-000 | Purchase Order | No | 0 | 3466 | 3466
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-07 | 1025902 - Arches0152 - 24004 Camino Oceano 24004 Camino Oceano | 0152/ | 1 | B | L | 2026-03-08 | Painting - Interior / Prep & Enamel (437206) (INT) [LS] [578700 - 34749823-000] [OP] | 2025-12-08 | 34749823-000 | Purchase Order | No | 0 | 1972.91 | 1972.91
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-07 | 1025902 - Arches0152 - 24004 Camino Oceano 24004 Camino Oceano | 0152/ | 1 | B | L | 2026-03-13 | Painting - Base Shoe (Flooring Orders) (437210) (INT) [LS] [578700 - 34748520-000] [OP] | 2025-12-08 | 34748520-000 | Purchase Order | No | 0 | 2243.45 | 2243.45
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-07 | 1025902 - Arches0152 - 24004 Camino Oceano 24004 Camino Oceano | 0152/ | 1 | B | L | 2026-03-18 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-08 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-10 | 1025903 - Arches0153 - 24006 Camino Oceano 24006 Camino Oceano | 0153/ | 1 | B | UNKWN | 2026-03-11 | Painting - Exterior Prime/Fascia (437229) (EXT) [LS] [578700 - 34749735-000] [OP] | 2025-12-11 | 34749735-000 | Purchase Order | No | 0 | 1944.82 | 1944.82
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-10 | 1025903 - Arches0153 - 24006 Camino Oceano 24006 Camino Oceano | 0153/ | 1 | B | UNKWN | 2026-03-16 | Painting - Interior / Prep & Enamel (437243) (INT) [LS] [578700 - 34742504-000] [OP] | 2025-12-11 | 34742504-000 | Purchase Order | No | 0 | 3949.98 | 3949.98
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-10 | 1025903 - Arches0153 - 24006 Camino Oceano 24006 Camino Oceano | 0153/ | 1 | B | UNKWN | 2026-03-21 | Painting - Exterior (437214) (EXT) [LS] [578700 - 34704207-000] [OP] | 2025-12-11 | 34704207-000 | Purchase Order | No | 0 | 3817.66 | 3817.66
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-10 | 1025903 - Arches0153 - 24006 Camino Oceano 24006 Camino Oceano | 0153/ | 1 | B | UNKWN | 2026-03-26 | Painting - Exterior / Prep & Enamel (437217) (INT) [LS] [578700 - 34708675-000] [OP] | 2025-12-11 | 34708675-000 | Purchase Order | No | 0 | 1738.44 | 1738.44
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-13 | 1025904 - Arches0154 - 24008 Camino Oceano 24008 Camino Oceano | 0154/ | 5 | C | R | 2026-03-14 | Painting - Exterior / Prep & Enamel (437241) (INT) [LS] [578700 - 34760142-000] [OP] | 2025-12-14 | 34760142-000 | Purchase Order | No | 0 | 1500.05 | 1500.05
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-13 | 1025904 - Arches0154 - 24008 Camino Oceano 24008 Camino Oceano | 0154/ | 5 | C | R | 2026-03-19 | Painting - Exterior Prime/Fascia (437215) (EXT) [LS] [578700 - 34797647-000] [OP] | 2025-12-14 | 34797647-000 | Purchase Order | No | 0 | 2964.79 | 2964.79
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-13 | 1025904 - Arches0154 - 24008 Camino Oceano 24008 Camino Oceano | 0154/ | 5 | C | R | 2026-03-24 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-14 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-13 | 1025904 - Arches0154 - 24008 Camino Oceano 24008 Camino Oceano | 0154/ | 5 | C | R | 2026-03-29 | Painting - Exterior / Prep & Enamel (437237) (INT) [LS] [578700 - 34752350-000] [OP] | 2025-12-14 | 34752350-000 | Purchase Order | No | 0 | 2266.99 | 2266.99
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-13 | 1025904 - Arches0154 - 24008 Camino Oceano 24008 Camino Oceano | 0154/ | 5 | C | R | 2026-04-03 | Painting - Exterior Prime/Fascia (437232) (EXT) [LS] [578700 - 34764686-000] [OP] | 2025-12-14 | 34764686-000 | Purchase Order | No | 0 | 1318.18 | 1318.18
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-13 | 1025904 - Arches0154 - 24008 Camino Oceano 24008 Camino Oceano | 0154/ | 5 | C | R | 2026-04-08 | Painting - Exterior (437207) (EXT) [LS] [578700 - 34720033-000] [OP] | 2025-12-14 | 34720033-000 | Purchase Order | No | 0 | 3196.06 | 3196.06
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-16 | 1025905 - Arches0155 - 24010 Camino Oceano 24010 Camino Oceano | 0155/ | 4 | A | L | 2026-03-17 | Painting - Touch Up (437233) (INT) [LS] [578700 - 34732953-000] [OP] | 2025-12-17 | 34732953-000 | Purchase Order | No | 0 | 4398.77 | 4398.77
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-16 | 1025905 - Arches0155 - 24010 Camino Oceano 24010 Camino Oceano | 0155/ | 4 | A | L | 2026-03-22 | Painting - Exterior (437243) (EXT) [LS] [578700 - 34794466-000] [OP] | 2025-12-17 | 34794466-000 | Purchase Order | No | 0 | 1400.93 | 1400.93
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-16 | 1025905 - Arches0155 - 24010 Camino Oceano 24010 Camino Oceano | 0155/ | 4 | A | L | 2026-03-27 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-17 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-16 | 1025905 - Arches0155 - 24010 Camino Oceano 24010 Camino Oceano | 0155/ | 4 | A | L | 2026-04-01 | Painting - Base Shoe (Flooring Orders) (437207) (INT) [LS] [578700 - 34738469-000] [OP] | 2025-12-17 | 34738469-000 | Purchase Order | No | 0 | 2521.68 | 2521.68
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-16 | 1025905 - Arches0155 - 24010 Camino Oceano 24010 Camino Oceano | 0155/ | 4 | A | L | 2026-04-06 | Painting - Touch Up (437200) (INT) [LS] [578700 - 34794646-000] [OP] | 2025-12-17 | 34794646-000 | Purchase Order | No | 0 | 4065.49 | 4065.49
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-16 | 1025905 - Arches0155 - 24010 Camino Oceano 24010 Camino Oceano | 0155/ | 4 | A | L | 2026-04-11 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-17 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-19 | 1025906 - Arches0156 - 24012 Camino Oceano 24012 Camino Oceano | 0156/ | 2 | A | UNKWN | 2026-03-20 | Painting - Interior / Prep & Enamel (437209) (INT) [LS] [578700 - 34749009-000] [OP] | 2025-12-20 | 34749009-000 | Purchase Order | No | 0 | 3668.79 | 3668.79
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-19 | 1025906 - Arches0156 - 24012 Camino Oceano 24012 Camino Oceano | 0156/ | 2 | A | UNKWN | 2026-03-25 | Painting - Exterior (437238) (EXT) [LS] [578700 - 34742487-000] [OP] | 2025-12-20 | 34742487-000 | Purchase Order | No | 0 | 2710.12 | 2710.12
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-19 | 1025906 - Arches0156 - 24012 Camino Oceano 24012 Camino Oceano | 0156/ | 2 | A | UNKWN | 2026-03-30 | Painting - Exterior (437223) (EXT) [578700 - 34740306-000] [UA] | 2025-12-20 | 34740306-000 | EPO | Yes | 0 | 819.73 | 819.73
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-19 | 1025906 - Arches0156 - 24012 Camino Oceano 24012 Camino Oceano | 0156/ | 2 | A | UNKWN | 2026-04-04 | Painting - Interior / Prep & Enamel (437236) (INT) [LS] [578700 - 34710322-000] [OP] | 2025-12-20 | 34710322-000 | Purchase Order | No | 0 | 1299.79 | 1299.79
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-19 | 1025906 - Arches0156 - 24012 Camino Oceano 24012 Camino Oceano | 0156/ | 2 | A | UNKWN | 2026-04-09 | Painting - Touch Up (437204) (INT) [LS] [578700 - 34799693-000] [OP] | 2025-12-20 | 34799693-000 | Purchase Order | No | 0 | 2864.47 | 2864.47
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-22 | 1025907 - Arches0157 - 24014 Camino Oceano 24014 Camino Oceano | 0157/ | 2 | B | UNKWN | 2026-03-23 | Painting - Exterior Prime/Fascia (437216) (EXT) [LS] [578700 - 34769163-000] [OP] | 2025-12-23 | 34769163-000 | Purchase Order | No | 0 | 4053.52 | 4053.52
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-22 | 1025907 - Arches0157 - 24014 Camino Oceano 24014 Camino Oceano | 0157/ | 2 | B | UNKWN | 2026-03-28 | Painting - Exterior / Prep & Enamel (437213) (INT) [LS] [578700 - 34770686-000] [OP] | 2025-12-23 | 34770686-000 | Purchase Order | No | 0 | 3643.43 | 3643.43
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-22 | 1025907 - Arches0157 - 24014 Camino Oceano 24014 Camino Oceano | 0157/ | 2 | B | UNKWN | 2026-04-02 | Painting - Interior / Prep & Enamel (437245) (INT) [LS] [578700 - 34740857-000] [OP] | 2025-12-23 | 34740857-000 | Purchase Order | No | 0 | 2396.47 | 2396.47
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-22 | 1025907 - Arches0157 - 24014 Camino Oceano 24014 Camino Oceano | 0157/ | 2 | B | UNKWN | 2026-04-07 | Painting - Base Shoe (Flooring Orders) (437228) (INT) [LS] [578700 - 34767839-000] [OP] | 2025-12-23 | 34767839-000 | Purchase Order | No | 0 | 2580.2 | 2580.2
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-22 | 1025907 - Arches0157 - 24014 Camino Oceano 24014 Camino Oceano | 0157/ | 2 | B | UNKWN | 2026-04-12 | Painting - Interior / Prep & Enamel (437214) (INT) [LS] [578700 - 34708392-000] [OP] | 2025-12-23 | 34708392-000 | Purchase Order | No | 0 | 2183.3 | 2183.3
Lennar Corporation - Lennar Orange County | OCH - Arches - 1157451 | PRODUCTION/WARRANTY | PH07 - HS 0044-0049, 0144-0142 (NOV) | 2026-01-22 | 1025907 - Arches0157 - 24014 Camino Oceano 24014 Camino Oceano | 0157/ | 2 | B | UNKWN | 2026-04-17 | Painting - Interior / Prep & Enamel (437237) (INT) [LS] [578700 - 34728864-000] [OP] | 2025-12-23 | 34728864-000 | Purchase Order | No | 0 | 1025.17 | 1025.17