## Sheet
Future Orders
Account: | Lennar Corporation - Lennar Orange County | Plan: | -- All -- | EPO: | -- All --
Subdvision: | OCH - Palms - 2234567 | Job Address: | -- All -- | Future Days: | 90
Phase: | PRODUCTION/WARRANTY | Builder's Order #: |  | Look Back Days: | -- All Scheduled Tasks --
Group: | PH03 - HS 0101-0110 (JAN) | Order Type: | -- All --
Account | Subdivision | Phase | Group | Job Start Date | Job | Lot/Block | Plan | Elevation | Swing | Task Start Date | Task | PO Contract Date | Builder's Order # | Order Type | EPO | Tax Amount | Job Subtotal Tax (Excl Tax) | Total
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-01 | 1025900 - Palms0200 - 24000 Camino Oceano 24000 Camino Oceano | 0200/ | 1 | B | R | 2026-03-02 | Painting - Base Shoe (Flooring Orders) (437204) (INT) [LS] [578700 - 34767391-000] [OP] | 2025-12-02 | 34767391-000 | Purchase Order | No | 0 | 1833.02 | 1833.02
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-01 | 1025900 - Palms0200 - 24000 Camino Oceano 24000 Camino Oceano | 0200/ | 1 | B | R | 2026-03-07 | Painting - Touch Up (437213) (INT) [LS] [578700 - 34770678-000] [OP] | 2025-12-02 | 34770678-000 | Purchase Order | No | 0 | 1463.09 | 1463.09
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-01 | 1025900 - Palms0200 - 24000 Camino Oceano 24000 Camino Oceano | 0200/ | 1 | B | R | 2026-03-12 | Painting - Touch Up (437215) (INT) [LS] [578700 - 34761993-000] [OP] | 2025-12-02 | 34761993-000 | Purchase Order | No | 0 | 3826.24 | 3826.24
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-04 | 1025901 - Palms0201 - 24002 Camino Oceano 24002 Camino Oceano | 0201/ | 2 | A | R | 2026-03-05 | Painting - Base Shoe (Flooring Orders) (437227) (INT) [LS] [578700 - 34753883-000] [OP] | 2025-12-05 | 34753883-000 | Purchase Order | No | 0 | 2634.59 | 2634.59
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-04 | 1025901 - Palms0201 - 24002 Camino Oceano 24002 Camino Oceano | 0201/ | 2 | A | R | 2026-03-10 | Painting - Exterior (437243) (EXT) [LS] [578700 - 34785649-000] [OP] | 2025-12-05 | 34785649-000 | Purchase Order | No | 0 | 4444.58 | 4444.58
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-04 | 1025901 - Palms0201 - 24002 Camino Oceano 24002 Camino Oceano | 0201/ | 2 | A | R | 2026-03-15 | Painting - Exterior (437203) (EXT) [578700 - 34752772-000] [UA] | 2025-12-05 | 34752772-000 | EPO | Yes | 0 | 1064.11 | 1064.11
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-04 | 1025901 - Palms0201 - 24002 Camino Oceano 24002 Camino Oceano | 0201/ | 2 | A | R | 2026-03-20 | Painting - Exterior (437215) (EXT) [578700 - 34725112-000] [UA] | 2025-12-05 | 34725112-000 | EPO | Yes | 0 | 795.1 | 795.1
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-04 | 1025901 - Palms0201 - 24002 Camino Oceano 24002 Camino Oceano | 0201/ | 2 | A | R | 2026-03-25 | Painting - Touch Up (437208) (INT) [LS] [578700 - 34755296-000] [OP] | 2025-12-05 | 34755296-000 | Purchase Order | No | 0 | 1642.21 | 1642.21
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-04 | 1025901 - Palms0201 - 24002 Camino Oceano 24002 Camino Oceano | 0201/ | 2 | A | R | 2026-03-30 | Painting - Touch Up (437215) (INT) [LS] [578700 - 34709880-000] [OP] | 2025-12-05 | 34709880-000 | Purchase Order | No | 0 | 2550.96 | 2550.96
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-07 | 1025902 - Palms0202 - 24004 Camino Oceano 24004 Camino Oceano | 0202/ | 5 | A | R | 2026-03-08 | Painting - Exterior (437248) (EXT) [578700 - 34730982-000] [UA] | 2025-12-08 | 34730982-000 | EPO | Yes | 0 | 783.16 | 783.16
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-07 | 1025902 - Palms0202 - 24004 Camino Oceano 24004 Camino Oceano | 0202/ | 5 | A | R | 2026-03-13 | Painting - Touch Up (437230) (INT) [LS] [578700 - 34728016-000] [OP] | 2025-12-08 | 34728016-000 | Purchase Order | No | 0 | 4026.28 | 4026.28
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-07 | 1025902 - Palms0202 - 24004 Camino Oceano 24004 Camino Oceano | 0202/ | 5 | A | R | 2026-03-18 | Painting - Exterior (437210) (EXT) [LS] [578700 - 34749672-000] [OP] | 2025-12-08 | 34749672-000 | Purchase Order | No | 0 | 1007.54 | 1007.54
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-10 | 1025903 - Palms0203 - 24006 Camino Oceano 24006 Camino Oceano | 0203/ | 4 | C | L | 2026-03-11 | Painting - Exterior / Prep & Enamel (437244) (INT) [LS] [578700 - 34795748-000] [OP] | 2025-12-11 | 34795748-000 | Purchase Order | No | 0 | 4483.98 | 4483.98
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-10 | 1025903 - Palms0203 - 24006 Camino Oceano 24006 Camino Oceano | 0203/ | 4 | C | L | 2026-03-16 | Painting - Touch Up (437209) (INT) [LS] [578700 - 34724890-000] [OP] | 2025-12-11 | 34724890-000 | Purchase Order | No | 0 | 2038.48 | 2038.48
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-10 | 1025903 - Palms0203 - 24006 Camino Oceano 24006 Camino Oceano | 0203/ | 4 | C | L | 2026-03-21 | Painting - Exterior (437237) (EXT) [LS] [578700 - 34796434-000] [OP] | 2025-12-11 | 34796434-000 | Purchase Order | No | 0 | 2897.68 | 2897.68
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-10 | 1025903 - Palms0203 - 24006 Camino Oceano 24006 Camino Oceano | 0203/ | 4 | C | L | 2026-03-26 | Painting - Base Shoe (Flooring Orders) (437203) (INT) [LS] [578700 - 34706572-000] [OP] | 2025-12-11 | 34706572-000 | Purchase Order | No | 0 | 3044.62 | 3044.62
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-10 | 1025903 - Palms0203 - 24006 Camino Oceano 24006 Camino Oceano | 0203/ | 4 | C | L | 2026-03-31 | Painting - Exterior Prime/Fascia (437203) (EXT) [LS] [578700 - 34766562-000] [OP] | 2025-12-11 | 34766562-000 | Purchase Order | No | 0 | 1280.39 | 1280.39
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-13 | 1025904 - Palms0204 - 24008 Camino Oceano 24008 Camino Oceano | 0204/ | 2 | A | UNKWN | 2026-03-14 | Painting - Interior / Prep & Enamel (437225) (INT) [LS] [578700 - 34715713-000] [OP] | 2025-12-14 | 34715713-000 | Purchase Order | No | 0 | 4295.59 | 4295.59
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-13 | 1025904 - Palms0204 - 24008 Camino Oceano 24008 Camino Oceano | 0204/ | 2 | A | UNKWN | 2026-03-19 | Painting - Interior / Prep & Enamel (437237) (INT) [LS] [578700 - 34777924-000] [OP] | 2025-12-14 | 34777924-000 | Purchase Order | No | 0 | 1139.1 | 1139.1
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-13 | 1025904 - Palms0204 - 24008 Camino Oceano 24008 Camino Oceano | 0204/ | 2 | A | UNKWN | 2026-03-24 | Painting - Exterior (437226) (EXT) [578700 - 34786163-000] [UA] | 2025-12-14 | 34786163-000 | EPO | Yes | 0 | 991.84 | 991.84
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-16 | 1025905 - Palms0205 - 24010 Camino Oceano 24010 Camino Oceano | 0205/ | 5 | C | L | 2026-03-17 | Painting - Base Shoe (Flooring Orders) (437215) (INT) [LS] [578700 - 34734814-000] [OP] | 2025-12-17 | 34734814-000 | Purchase Order | No | 0 | 2385.25 | 2385.25
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-16 | 1025905 - Palms0205 - 24010 Camino Oceano 24010 Camino Oceano | 0205/ | 5 | C | L | 2026-03-22 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-17 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-16 | 1025905 - Palms0205 - 24010 Camino Oceano 24010 Camino Oceano | 0205/ | 5 | C | L | 2026-03-27 | Painting - Exterior (437200) (EXT) [578700 - 34760068-000] [UA] | 2025-12-17 | 34760068-000 | EPO | Yes | 0 | 1010.58 | 1010.58
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-16 | 1025905 - Palms0205 - 24010 Camino Oceano 24010 Camino Oceano | 0205/ | 5 | C | L | 2026-04-01 | Painting - Exterior (437204) (EXT) [578700 - 34770468-000] [UA] | 2025-12-17 | 34770468-000 | EPO | Yes | 0 | 806.58 | 806.58
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-19 | 1025906 - Palms0206 - 24012 Camino Oceano 24012 Camino Oceano | 0206/ | 3 | B | L | 2026-03-20 | Painting - Interior / Prep & Enamel (437223) (INT) [LS] [578700 - 34737353-000] [OP] | 2025-12-20 | 34737353-000 | Purchase Order | No | 0 | 1552.11 | 1552.11
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-19 | 1025906 - Palms0206 - 24012 Camino Oceano 24012 Camino Oceano | 0206/ | 3 | B | L | 2026-03-25 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-20 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-19 | 1025906 - Palms0206 - 24012 Camino Oceano 24012 Camino Oceano | 0206/ | 3 | B | L | 2026-03-30 | Painting - Exterior (437242) (EXT) [LS] [578700 - 34772692-000] [OP] | 2025-12-20 | 34772692-000 | Purchase Order | No | 0 | 2047.83 | 2047.83
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-22 | 1025907 - Palms0207 - 24014 Camino Oceano 24014 Camino Oceano | 0207/ | 1 | B | L | 2026-03-23 | Painting - Exterior (437247) (EXT) [578700 - 34772512-000] [UA] | 2025-12-23 | 34772512-000 | EPO | Yes | 0 | 777.72 | 777.72
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-22 | 1025907 - Palms0207 - 24014 Camino Oceano 24014 Camino Oceano | 0207/ | 1 | B | L | 2026-03-28 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-23 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-22 | 1025907 - Palms0207 - 24014 Camino Oceano 24014 Camino Oceano | 0207/ | 1 | B | L | 2026-04-02 | Painting - Base Shoe (Flooring Orders) (437213) (INT) [LS] [578700 - 34790111-000] [OP] | 2025-12-23 | 34790111-000 | Purchase Order | No | 0 | 3219.83 | 3219.83
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-25 | 1025908 - Palms0208 - 24016 Camino Oceano 24016 Camino Oceano | 0208/ | 3 | D | L | 2026-03-26 | Painting - Exterior (437240) (EXT) [578700 - 34755518-000] [UA] | 2025-12-26 | 34755518-000 | EPO | Yes | 0 | 1114.67 | 1114.67
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-25 | 1025908 - Palms0208 - 24016 Camino Oceano 24016 Camino Oceano | 0208/ | 3 | D | L | 2026-03-31 | Painting - Exterior (437200) (EXT) [LS] [578700 - 34743719-000] [OP] | 2025-12-26 | 34743719-000 | Purchase Order | No | 0 | 3698.92 | 3698.92
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-25 | 1025908 - Palms0208 - 24016 Camino Oceano 24016 Camino Oceano | 0208/ | 3 | D | L | 2026-04-05 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-26 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-28 | 1025909 - Palms0209 - 24018 Camino Oceano 24018 Camino Oceano | 0209/ | 4 | D | UNKWN | 2026-03-29 | Painting - Exterior (437204) (EXT) [578700 - 34790573-000] [UA] | 2025-12-29 | 34790573-000 | EPO | Yes | 0 | 1151.96 | 1151.96
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-28 | 1025909 - Palms0209 - 24018 Camino Oceano 24018 Camino Oceano | 0209/ | 4 | D | UNKWN | 2026-04-03 | Painting - Exterior (437223) (EXT) [LS] [578700 - 34776350-000] [OP] | 2025-12-29 | 34776350-000 | Purchase Order | No | 0 | 2933.84 | 2933.84
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-28 | 1025909 - Palms0209 - 24018 Camino Oceano 24018 Camino Oceano | 0209/ | 4 | D | UNKWN | 2026-04-08 | Painting - Exterior / Prep & Enamel (437208) (INT) [LS] [578700 - 34705482-000] [OP] | 2025-12-29 | 34705482-000 | Purchase Order | No | 0 | 2078.9 | 2078.9
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-31 | 1025910 - Palms0210 - 24020 Camino Oceano 24020 Camino Oceano | 0210/ | 1 | C | R | 2026-04-01 | Painting - Exterior (437222) (EXT) [578700 - 34773385-000] [UA] | 2026-01-01 | 34773385-000 | EPO | Yes | 0 | 1142.07 | 1142.07
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-31 | 1025910 - Palms0210 - 24020 Camino Oceano 24020 Camino Oceano | 0210/ | 1 | C | R | 2026-04-06 | Painting - Exterior / Prep & Enamel (437239) (INT) [LS] [578700 - 34798235-000] [OP] | 2026-01-01 | 34798235-000 | Purchase Order | No | 0 | 1540.94 | 1540.94
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-31 | 1025910 - Palms0210 - 24020 Camino Oceano 24020 Camino Oceano | 0210/ | 1 | C | R | 2026-04-11 | Painting - Interior / Prep & Enamel (437210) (INT) [LS] [578700 - 34723206-000] [OP] | 2026-01-01 | 34723206-000 | Purchase Order | No | 0 | 4084.96 | 4084.96
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-01-31 | 1025910 - Palms0210 - 24020 Camino Oceano 24020 Camino Oceano | 0210/ | 1 | C | R | 2026-04-16 | Painting - Exterior (437211) (EXT) [LS] [578700 - 34796542-000] [OP] | 2026-01-01 | 34796542-000 | Purchase Order | No | 0 | 4235.71 | 4235.71
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-02-03 | 1025911 - Palms0211 - 24022 Camino Oceano 24022 Camino Oceano | 0211/ | 4 | B | L | 2026-04-04 | Painting - Exterior (437224) (EXT) [578700 - 34705075-000] [UA] | 2026-01-04 | 34705075-000 | EPO | Yes | 0 | 1129.3 | 1129.3
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-02-03 | 1025911 - Palms0211 - 24022 Camino Oceano 24022 Camino Oceano | 0211/ | 4 | B | L | 2026-04-09 | Painting - Interior / Prep & Enamel (437212) (INT) [LS] [578700 - 34760332-000] [OP] | 2026-01-04 | 34760332-000 | Purchase Order | No | 0 | 2223.8 | 2223.8
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-02-03 | 1025911 - Palms0211 - 24022 Camino Oceano 24022 Camino Oceano | 0211/ | 4 | B | L | 2026-04-14 | Painting - Interior / Prep & Enamel (437214) (INT) [LS] [578700 - 34703101-000] [OP] | 2026-01-04 | 34703101-000 | Purchase Order | No | 0 | 3310.12 | 3310.12
Lennar Corporation - Lennar Orange County | OCH - Palms - 2234567 | PRODUCTION/WARRANTY | PH03 - HS 0101-0110 (JAN) | 2026-02-03 | 1025911 - Palms0211 - 24022 Camino Oceano 24022 Camino Oceano | 0211/ | 4 | B | L | 2026-04-19 | Painting - Exterior / Prep & Enamel (437221) (INT) [LS] [578700 - 34736517-000] [OP] | 2026-01-04 | 34736517-000 | Purchase Order | No | 0 | 4025.24 | 4025.24