## Sheet
Future Orders
Account: | Lennar Corporation - Lennar Orange County | Plan: | -- All -- | EPO: | -- All --
Subdvision: | OCH - Sunset Hills - 4456789 | Job Address: | -- All -- | Future Days: | 90
Phase: | PRODUCTION/WARRANTY | Builder's Order #: |  | Look Back Days: | -- All Scheduled Tasks --
Group: | PH05 - HS 0080-0095 (FEB) | Order Type: | -- All --
Account | Subdivision | Phase | Group | Job Start Date | Job | Lot/Block | Plan | Elevation | Swing | Task Start Date | Task | PO Contract Date | Builder's Order # | Order Type | EPO | Tax Amount | Job Subtotal Tax (Excl Tax) | Total
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-01 | 1025900 - Sunset Hills0300 - 24000 Camino Oceano 24000 Camino Oceano | 0300/ | 2 | B | L | 2026-03-02 | Painting - Interior / Prep & Enamel (437204) (INT) [LS] [578700 - 34754377-000] [OP] | 2025-12-02 | 34754377-000 | Purchase Order | No | 0 | 2426.6 | 2426.6
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-01 | 1025900 - Sunset Hills0300 - 24000 Camino Oceano 24000 Camino Oceano | 0300/ | 2 | B | L | 2026-03-07 | Painting - Touch Up (437226) (INT) [LS] [578700 - 34708161-000] [OP] | 2025-12-02 | 34708161-000 | Purchase Order | No | 0 | 1723.92 | 1723.92
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-01 | 1025900 - Sunset Hills0300 - 24000 Camino Oceano 24000 Camino Oceano | 0300/ | 2 | B | L | 2026-03-12 | Painting - Exterior / Prep & Enamel (437224) (INT) [LS] [578700 - 34776556-000] [OP] | 2025-12-02 | 34776556-000 | Purchase Order | No | 0 | 4311.22 | 4311.22
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-01 | 1025900 - Sunset Hills0300 - 24000 Camino Oceano 24000 Camino Oceano | 0300/ | 2 | B | L | 2026-03-17 | Painting - Exterior (437248) (EXT) [LS] [578700 - 34775456-000] [OP] | 2025-12-02 | 34775456-000 | Purchase Order | No | 0 | 2331.33 | 2331.33
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-04 | 1025901 - Sunset Hills0301 - 24002 Camino Oceano 24002 Camino Oceano | 0301/ | 1 | C | L | 2026-03-05 | Painting - Exterior / Prep & Enamel (437234) (INT) [LS] [578700 - 34797978-000] [OP] | 2025-12-05 | 34797978-000 | Purchase Order | No | 0 | 3571.22 | 3571.22
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-04 | 1025901 - Sunset Hills0301 - 24002 Camino Oceano 24002 Camino Oceano | 0301/ | 1 | C | L | 2026-03-10 | Painting - Interior / Prep & Enamel (437231) (INT) [LS] [578700 - 34728760-000] [OP] | 2025-12-05 | 34728760-000 | Purchase Order | No | 0 | 1955.27 | 1955.27
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-04 | 1025901 - Sunset Hills0301 - 24002 Camino Oceano 24002 Camino Oceano | 0301/ | 1 | C | L | 2026-03-15 | Painting - Touch Up (437201) (INT) [LS] [578700 - 34750968-000] [OP] | 2025-12-05 | 34750968-000 | Purchase Order | No | 0 | 2176.45 | 2176.45
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-04 | 1025901 - Sunset Hills0301 - 24002 Camino Oceano 24002 Camino Oceano | 0301/ | 1 | C | L | 2026-03-20 | Painting - Exterior / Prep & Enamel (437246) (INT) [LS] [578700 - 34721632-000] [OP] | 2025-12-05 | 34721632-000 | Purchase Order | No | 0 | 3941.77 | 3941.77
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-04 | 1025901 - Sunset Hills0301 - 24002 Camino Oceano 24002 Camino Oceano | 0301/ | 1 | C | L | 2026-03-25 | Painting - Exterior Prime/Fascia (437239) (EXT) [LS] [578700 - 34770008-000] [OP] | 2025-12-05 | 34770008-000 | Purchase Order | No | 0 | 1094.38 | 1094.38
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-04 | 1025901 - Sunset Hills0301 - 24002 Camino Oceano 24002 Camino Oceano | 0301/ | 1 | C | L | 2026-03-30 | Painting - Exterior / Prep & Enamel (437237) (INT) [LS] [578700 - 34773975-000] [OP] | 2025-12-05 | 34773975-000 | Purchase Order | No | 0 | 3320.5 | 3320.5
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-07 | 1025902 - Sunset Hills0302 - 24004 Camino Oceano 24004 Camino Oceano | 0302/ | 1 | D | R | 2026-03-08 | Painting - Exterior Prime/Fascia (437203) (EXT) [LS] [578700 - 34734099-000] [OP] | 2025-12-08 | 34734099-000 | Purchase Order | No | 0 | 2326.86 | 2326.86
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-07 | 1025902 - Sunset Hills0302 - 24004 Camino Oceano 24004 Camino Oceano | 0302/ | 1 | D | R | 2026-03-13 | Painting - Interior / Prep & Enamel (437229) (INT) [LS] [578700 - 34742840-000] [OP] | 2025-12-08 | 34742840-000 | Purchase Order | No | 0 | 2181.25 | 2181.25
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-07 | 1025902 - Sunset Hills0302 - 24004 Camino Oceano 24004 Camino Oceano | 0302/ | 1 | D | R | 2026-03-18 | Painting - Exterior / Prep & Enamel (437217) (INT) [LS] [578700 - 34798567-000] [OP] | 2025-12-08 | 34798567-000 | Purchase Order | No | 0 | 4329.21 | 4329.21
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-07 | 1025902 - Sunset Hills0302 - 24004 Camino Oceano 24004 Camino Oceano | 0302/ | 1 | D | R | 2026-03-23 | Painting - Exterior / Prep & Enamel (437216) (INT) [LS] [578700 - 34710735-000] [OP] | 2025-12-08 | 34710735-000 | Purchase Order | No | 0 | 2646.07 | 2646.07
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-07 | 1025902 - Sunset Hills0302 - 24004 Camino Oceano 24004 Camino Oceano | 0302/ | 1 | D | R | 2026-03-28 | Painting - Exterior (437222) (EXT) [LS] [578700 - 34729389-000] [OP] | 2025-12-08 | 34729389-000 | Purchase Order | No | 0 | 3275.5 | 3275.5
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-07 | 1025902 - Sunset Hills0302 - 24004 Camino Oceano 24004 Camino Oceano | 0302/ | 1 | D | R | 2026-04-02 | Painting - Exterior (437248) (EXT) [LS] [578700 - 34704067-000] [OP] | 2025-12-08 | 34704067-000 | Purchase Order | No | 0 | 4323.64 | 4323.64
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-10 | 1025903 - Sunset Hills0303 - 24006 Camino Oceano 24006 Camino Oceano | 0303/ | 2 | A | UNKWN | 2026-03-11 | Painting - Interior / Prep & Enamel (437208) (INT) [LS] [578700 - 34762070-000] [OP] | 2025-12-11 | 34762070-000 | Purchase Order | No | 0 | 3343.11 | 3343.11
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-10 | 1025903 - Sunset Hills0303 - 24006 Camino Oceano 24006 Camino Oceano | 0303/ | 2 | A | UNKWN | 2026-03-16 | Painting - Interior / Prep & Enamel (437229) (INT) [LS] [578700 - 34791680-000] [OP] | 2025-12-11 | 34791680-000 | Purchase Order | No | 0 | 1896.85 | 1896.85
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-10 | 1025903 - Sunset Hills0303 - 24006 Camino Oceano 24006 Camino Oceano | 0303/ | 2 | A | UNKWN | 2026-03-21 | Painting - Base Shoe (Flooring Orders) (437210) (INT) [LS] [578700 - 34779415-000] [OP] | 2025-12-11 | 34779415-000 | Purchase Order | No | 0 | 3125.37 | 3125.37
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-10 | 1025903 - Sunset Hills0303 - 24006 Camino Oceano 24006 Camino Oceano | 0303/ | 2 | A | UNKWN | 2026-03-26 | Painting - Exterior (437249) (EXT) [578700 - 34721465-000] [UA] | 2025-12-11 | 34721465-000 | EPO | Yes | 0 | 1182.36 | 1182.36
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-13 | 1025904 - Sunset Hills0304 - 24008 Camino Oceano 24008 Camino Oceano | 0304/ | 1 | A | L | 2026-03-14 | Painting - Exterior / Prep & Enamel (437245) (INT) [LS] [578700 - 34725995-000] [OP] | 2025-12-14 | 34725995-000 | Purchase Order | No | 0 | 1265.99 | 1265.99
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-13 | 1025904 - Sunset Hills0304 - 24008 Camino Oceano 24008 Camino Oceano | 0304/ | 1 | A | L | 2026-03-19 | Painting - Interior / Prep & Enamel (437206) (INT) [LS] [578700 - 34791382-000] [OP] | 2025-12-14 | 34791382-000 | Purchase Order | No | 0 | 3703.68 | 3703.68
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-13 | 1025904 - Sunset Hills0304 - 24008 Camino Oceano 24008 Camino Oceano | 0304/ | 1 | A | L | 2026-03-24 | Painting - Exterior (437250) (EXT) [578700 - 34774177-000] [UA] | 2025-12-14 | 34774177-000 | EPO | Yes | 0 | 1091.32 | 1091.32
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-13 | 1025904 - Sunset Hills0304 - 24008 Camino Oceano 24008 Camino Oceano | 0304/ | 1 | A | L | 2026-03-29 | Painting - Base Shoe (Flooring Orders) (437234) (INT) [LS] [578700 - 34756148-000] [OP] | 2025-12-14 | 34756148-000 | Purchase Order | No | 0 | 3315.32 | 3315.32
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-13 | 1025904 - Sunset Hills0304 - 24008 Camino Oceano 24008 Camino Oceano | 0304/ | 1 | A | L | 2026-04-03 | Painting - Exterior (437232) (EXT) [578700 - 34784874-000] [UA] | 2025-12-14 | 34784874-000 | EPO | Yes | 0 | 870.62 | 870.62
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-13 | 1025904 - Sunset Hills0304 - 24008 Camino Oceano 24008 Camino Oceano | 0304/ | 1 | A | L | 2026-04-08 | Painting - Exterior / Prep & Enamel (437231) (INT) [LS] [578700 - 34713833-000] [OP] | 2025-12-14 | 34713833-000 | Purchase Order | No | 0 | 2517.33 | 2517.33
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-16 | 1025905 - Sunset Hills0305 - 24010 Camino Oceano 24010 Camino Oceano | 0305/ | 3 | D | UNKWN | 2026-03-17 | Painting - Exterior / Prep & Enamel (437211) (INT) [LS] [578700 - 34796180-000] [OP] | 2025-12-17 | 34796180-000 | Purchase Order | No | 0 | 2826.11 | 2826.11
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-16 | 1025905 - Sunset Hills0305 - 24010 Camino Oceano 24010 Camino Oceano | 0305/ | 3 | D | UNKWN | 2026-03-22 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-17 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-16 | 1025905 - Sunset Hills0305 - 24010 Camino Oceano 24010 Camino Oceano | 0305/ | 3 | D | UNKWN | 2026-03-27 | Painting - Touch Up (437229) (INT) [LS] [578700 - 34757091-000] [OP] | 2025-12-17 | 34757091-000 | Purchase Order | No | 0 | 3890.07 | 3890.07
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-16 | 1025905 - Sunset Hills0305 - 24010 Camino Oceano 24010 Camino Oceano | 0305/ | 3 | D | UNKWN | 2026-04-01 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-17 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-19 | 1025906 - Sunset Hills0306 - 24012 Camino Oceano 24012 Camino Oceano | 0306/ | 1 | C | L | 2026-03-20 | Painting - Touch Up (437236) (INT) [LS] [578700 - 34779997-000] [OP] | 2025-12-20 | 34779997-000 | Purchase Order | No | 0 | 3338.66 | 3338.66
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-19 | 1025906 - Sunset Hills0306 - 24012 Camino Oceano 24012 Camino Oceano | 0306/ | 1 | C | L | 2026-03-25 | Painting - Base Shoe (Flooring Orders) (437201) (INT) [LS] [578700 - 34764789-000] [OP] | 2025-12-20 | 34764789-000 | Purchase Order | No | 0 | 3978.33 | 3978.33
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-19 | 1025906 - Sunset Hills0306 - 24012 Camino Oceano 24012 Camino Oceano | 0306/ | 1 | C | L | 2026-03-30 | Painting - Exterior Prime/Fascia (437231) (EXT) [LS] [578700 - 34727802-000] [OP] | 2025-12-20 | 34727802-000 | Purchase Order | No | 0 | 2241.89 | 2241.89
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-19 | 1025906 - Sunset Hills0306 - 24012 Camino Oceano 24012 Camino Oceano | 0306/ | 1 | C | L | 2026-04-04 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-20 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-22 | 1025907 - Sunset Hills0307 - 24014 Camino Oceano 24014 Camino Oceano | 0307/ | 5 | C | UNKWN | 2026-03-23 | Painting - Interior / Prep & Enamel (437205) (INT) [LS] [578700 - 34731635-000] [OP] | 2025-12-23 | 34731635-000 | Purchase Order | No | 0 | 3520.26 | 3520.26
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-22 | 1025907 - Sunset Hills0307 - 24014 Camino Oceano 24014 Camino Oceano | 0307/ | 5 | C | UNKWN | 2026-03-28 | Painting - Touch Up (437235) (INT) [LS] [578700 - 34799374-000] [OP] | 2025-12-23 | 34799374-000 | Purchase Order | No | 0 | 1841.13 | 1841.13
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-22 | 1025907 - Sunset Hills0307 - 24014 Camino Oceano 24014 Camino Oceano | 0307/ | 5 | C | UNKWN | 2026-04-02 | Painting - Touch Up (437241) (INT) [LS] [578700 - 34793302-000] [OP] | 2025-12-23 | 34793302-000 | Purchase Order | No | 0 | 2717.87 | 2717.87
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-25 | 1025908 - Sunset Hills0308 - 24016 Camino Oceano 24016 Camino Oceano | 0308/ | 1 | A | L | 2026-03-26 | Painting - Exterior / Prep & Enamel (437244) (INT) [LS] [578700 - 34731890-000] [OP] | 2025-12-26 | 34731890-000 | Purchase Order | No | 0 | 2071.72 | 2071.72
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-25 | 1025908 - Sunset Hills0308 - 24016 Camino Oceano 24016 Camino Oceano | 0308/ | 1 | A | L | 2026-03-31 | Painting - Base Shoe (Flooring Orders) (437230) (INT) [LS] [578700 - 34772544-000] [OP] | 2025-12-26 | 34772544-000 | Purchase Order | No | 0 | 2858.23 | 2858.23
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-25 | 1025908 - Sunset Hills0308 - 24016 Camino Oceano 24016 Camino Oceano | 0308/ | 1 | A | L | 2026-04-05 | Painting - Exterior / Prep & Enamel (437247) (INT) [LS] [578700 - 34772140-000] [OP] | 2025-12-26 | 34772140-000 | Purchase Order | No | 0 | 2157.77 | 2157.77
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-25 | 1025908 - Sunset Hills0308 - 24016 Camino Oceano 24016 Camino Oceano | 0308/ | 1 | A | L | 2026-04-10 | Painting - Touch Up (437217) (INT) [LS] [578700 - 34740189-000] [OP] | 2025-12-26 | 34740189-000 | Purchase Order | No | 0 | 1879.91 | 1879.91
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-28 | 1025909 - Sunset Hills0309 - 24018 Camino Oceano 24018 Camino Oceano | 0309/ | 1 | B | L | 2026-03-29 | Painting - Exterior Prime/Fascia (437212) (EXT) [LS] [578700 - 34728361-000] [OP] | 2025-12-29 | 34728361-000 | Purchase Order | No | 0 | 3585.12 | 3585.12
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-28 | 1025909 - Sunset Hills0309 - 24018 Camino Oceano 24018 Camino Oceano | 0309/ | 1 | B | L | 2026-04-03 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-29 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-28 | 1025909 - Sunset Hills0309 - 24018 Camino Oceano 24018 Camino Oceano | 0309/ | 1 | B | L | 2026-04-08 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-29 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-31 | 1025910 - Sunset Hills0310 - 24020 Camino Oceano 24020 Camino Oceano | 0310/ | 3 | B | L | 2026-04-01 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2026-01-01 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-31 | 1025910 - Sunset Hills0310 - 24020 Camino Oceano 24020 Camino Oceano | 0310/ | 3 | B | L | 2026-04-06 | Painting - Exterior Prime/Fascia (437217) (EXT) [LS] [578700 - 34705965-000] [OP] | 2026-01-01 | 34705965-000 | Purchase Order | No | 0 | 4410.03 | 4410.03
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-31 | 1025910 - Sunset Hills0310 - 24020 Camino Oceano 24020 Camino Oceano | 0310/ | 3 | B | L | 2026-04-11 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2026-01-01 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-01-31 | 1025910 - Sunset Hills0310 - 24020 Camino Oceano 24020 Camino Oceano | 0310/ | 3 | B | L | 2026-04-16 | Painting - Touch Up (437206) (INT) [LS] [578700 - 34701607-000] [OP] | 2026-01-01 | 34701607-000 | Purchase Order | No | 0 | 3009.22 | 3009.22
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-03 | 1025911 - Sunset Hills0311 - 24022 Camino Oceano 24022 Camino Oceano | 0311/ | 4 | D | L | 2026-04-04 | Painting - Exterior Prime/Fascia (437203) (EXT) [LS] [578700 - 34733092-000] [OP] | 2026-01-04 | 34733092-000 | Purchase Order | No | 0 | 4293.72 | 4293.72
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-03 | 1025911 - Sunset Hills0311 - 24022 Camino Oceano 24022 Camino Oceano | 0311/ | 4 | D | L | 2026-04-09 | Painting - Touch Up (437207) (INT) [LS] [578700 - 34708564-000] [OP] | 2026-01-04 | 34708564-000 | Purchase Order | No | 0 | 2402.48 | 2402.48
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-03 | 1025911 - Sunset Hills0311 - 24022 Camino Oceano 24022 Camino Oceano | 0311/ | 4 | D | L | 2026-04-14 | Painting - Exterior (437236) (EXT) [578700 - 34782502-000] [UA] | 2026-01-04 | 34782502-000 | EPO | Yes | 0 | 1043.23 | 1043.23
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-03 | 1025911 - Sunset Hills0311 - 24022 Camino Oceano 24022 Camino Oceano | 0311/ | 4 | D | L | 2026-04-19 | Painting - Exterior Prime/Fascia (437209) (EXT) [LS] [578700 - 34773772-000] [OP] | 2026-01-04 | 34773772-000 | Purchase Order | No | 0 | 4321.94 | 4321.94
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-03 | 1025911 - Sunset Hills0311 - 24022 Camino Oceano 24022 Camino Oceano | 0311/ | 4 | D | L | 2026-04-24 | Painting - Exterior (437215) (EXT) [578700 - 34715525-000] [UA] | 2026-01-04 | 34715525-000 | EPO | Yes | 0 | 979.04 | 979.04
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-06 | 1025912 - Sunset Hills0312 - 24024 Camino Oceano 24024 Camino Oceano | 0312/ | 4 | B | UNKWN | 2026-04-07 | Painting - Touch Up (437228) (INT) [LS] [578700 - 34738974-000] [OP] | 2026-01-07 | 34738974-000 | Purchase Order | No | 0 | 4010.58 | 4010.58
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-06 | 1025912 - Sunset Hills0312 - 24024 Camino Oceano 24024 Camino Oceano | 0312/ | 4 | B | UNKWN | 2026-04-12 | Painting - Exterior / Prep & Enamel (437219) (INT) [LS] [578700 - 34774531-000] [OP] | 2026-01-07 | 34774531-000 | Purchase Order | No | 0 | 3173.6 | 3173.6
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-06 | 1025912 - Sunset Hills0312 - 24024 Camino Oceano 24024 Camino Oceano | 0312/ | 4 | B | UNKWN | 2026-04-17 | Painting - Exterior (437248) (EXT) [578700 - 34727235-000] [UA] | 2026-01-07 | 34727235-000 | EPO | Yes | 0 | 1012.76 | 1012.76
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-06 | 1025912 - Sunset Hills0312 - 24024 Camino Oceano 24024 Camino Oceano | 0312/ | 4 | B | UNKWN | 2026-04-22 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2026-01-07 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-06 | 1025912 - Sunset Hills0312 - 24024 Camino Oceano 24024 Camino Oceano | 0312/ | 4 | B | UNKWN | 2026-04-27 | Painting - Exterior Prime/Fascia (437215) (EXT) [LS] [578700 - 34722782-000] [OP] | 2026-01-07 | 34722782-000 | Purchase Order | No | 0 | 2931.97 | 2931.97
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-06 | 1025912 - Sunset Hills0312 - 24024 Camino Oceano 24024 Camino Oceano | 0312/ | 4 | B | UNKWN | 2026-05-02 | Painting - Exterior Prime/Fascia (437200) (EXT) [LS] [578700 - 34753545-000] [OP] | 2026-01-07 | 34753545-000 | Purchase Order | No | 0 | 2576.76 | 2576.76
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-09 | 1025913 - Sunset Hills0313 - 24026 Camino Oceano 24026 Camino Oceano | 0313/ | 5 | D | L | 2026-04-10 | Painting - Interior / Prep & Enamel (437218) (INT) [LS] [578700 - 34792662-000] [OP] | 2026-01-10 | 34792662-000 | Purchase Order | No | 0 | 1989.51 | 1989.51
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-09 | 1025913 - Sunset Hills0313 - 24026 Camino Oceano 24026 Camino Oceano | 0313/ | 5 | D | L | 2026-04-15 | Painting - Touch Up (437204) (INT) [LS] [578700 - 34790096-000] [OP] | 2026-01-10 | 34790096-000 | Purchase Order | No | 0 | 1816.98 | 1816.98
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-09 | 1025913 - Sunset Hills0313 - 24026 Camino Oceano 24026 Camino Oceano | 0313/ | 5 | D | L | 2026-04-20 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2026-01-10 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-12 | 1025914 - Sunset Hills0314 - 24028 Camino Oceano 24028 Camino Oceano | 0314/ | 5 | B | L | 2026-04-13 | Painting - Interior / Prep & Enamel (437241) (INT) [LS] [578700 - 34719528-000] [OP] | 2026-01-13 | 34719528-000 | Purchase Order | No | 0 | 4179.44 | 4179.44
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-12 | 1025914 - Sunset Hills0314 - 24028 Camino Oceano 24028 Camino Oceano | 0314/ | 5 | B | L | 2026-04-18 | Painting - Exterior Prime/Fascia (437204) (EXT) [LS] [578700 - 34707816-000] [OP] | 2026-01-13 | 34707816-000 | Purchase Order | No | 0 | 1580.73 | 1580.73
Lennar Corporation - Lennar Orange County | OCH - Sunset Hills - 4456789 | PRODUCTION/WARRANTY | PH05 - HS 0080-0095 (FEB) | 2026-02-12 | 1025914 - Sunset Hills0314 - 24028 Camino Oceano 24028 Camino Oceano | 0314/ | 5 | B | L | 2026-04-23 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2026-01-13 |  | Memo | No | 0 | 0 | 0