## Sheet
Future Orders
Account: | Lennar Corporation - Lennar Orange County | Plan: | -- All -- | EPO: | -- All --
Subdvision: | OCH - Canyon View - 5567890 | Job Address: | -- All -- | Future Days: | 90
Phase: | PRODUCTION/WARRANTY | Builder's Order #: |  | Look Back Days: | -- All Scheduled Tasks --
Group: | PH09 - HS 0150-0175 (APR) | Order Type: | -- All --
Account | Subdivision | Phase | Group | Job Start Date | Job | Lot/Block | Plan | Elevation | Swing | Task Start Date | Task | PO Contract Date | Builder's Order # | Order Type | EPO | Tax Amount | Job Subtotal Tax (Excl Tax) | Total
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-01 | 1025900 - Canyon View0350 - 24000 Camino Oceano 24000 Camino Oceano | 0350/ | 5 | C | L | 2026-03-02 | Painting - Touch Up (437244) (INT) [LS] [578700 - 34739857-000] [OP] | 2025-12-02 | 34739857-000 | Purchase Order | No | 0 | 3449.07 | 3449.07
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-01 | 1025900 - Canyon View0350 - 24000 Camino Oceano 24000 Camino Oceano | 0350/ | 5 | C | L | 2026-03-07 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-02 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-01 | 1025900 - Canyon View0350 - 24000 Camino Oceano 24000 Camino Oceano | 0350/ | 5 | C | L | 2026-03-12 | Painting - Touch Up (437228) (INT) [LS] [578700 - 34710543-000] [OP] | 2025-12-02 | 34710543-000 | Purchase Order | No | 0 | 3093.13 | 3093.13
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-04 | 1025901 - Canyon View0351 - 24002 Camino Oceano 24002 Camino Oceano | 0351/ | 4 | C | UNKWN | 2026-03-05 | Painting - Exterior (437205) (EXT) [LS] [578700 - 34730005-000] [OP] | 2025-12-05 | 34730005-000 | Purchase Order | No | 0 | 4366.69 | 4366.69
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-04 | 1025901 - Canyon View0351 - 24002 Camino Oceano 24002 Camino Oceano | 0351/ | 4 | C | UNKWN | 2026-03-10 | Painting - Exterior (437248) (EXT) [LS] [578700 - 34788117-000] [OP] | 2025-12-05 | 34788117-000 | Purchase Order | No | 0 | 3874.97 | 3874.97
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-04 | 1025901 - Canyon View0351 - 24002 Camino Oceano 24002 Camino Oceano | 0351/ | 4 | C | UNKWN | 2026-03-15 | Painting - Exterior (437248) (EXT) [LS] [578700 - 34799125-000] [OP] | 2025-12-05 | 34799125-000 | Purchase Order | No | 0 | 1613.17 | 1613.17
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-04 | 1025901 - Canyon View0351 - 24002 Camino Oceano 24002 Camino Oceano | 0351/ | 4 | C | UNKWN | 2026-03-20 | Painting - Touch Up (437217) (INT) [LS] [578700 - 34723788-000] [OP] | 2025-12-05 | 34723788-000 | Purchase Order | No | 0 | 4489.31 | 4489.31
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-04 | 1025901 - Canyon View0351 - 24002 Camino Oceano 24002 Camino Oceano | 0351/ | 4 | C | UNKWN | 2026-03-25 | Painting - Exterior / Prep & Enamel (437240) (INT) [LS] [578700 - 34764451-000] [OP] | 2025-12-05 | 34764451-000 | Purchase Order | No | 0 | 4391.69 | 4391.69
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-07 | 1025902 - Canyon View0352 - 24004 Camino Oceano 24004 Camino Oceano | 0352/ | 4 | C | L | 2026-03-08 | Painting - Base Shoe (Flooring Orders) (437242) (INT) [LS] [578700 - 34713710-000] [OP] | 2025-12-08 | 34713710-000 | Purchase Order | No | 0 | 4002.07 | 4002.07
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-07 | 1025902 - Canyon View0352 - 24004 Camino Oceano 24004 Camino Oceano | 0352/ | 4 | C | L | 2026-03-13 | Painting - Base Shoe (Flooring Orders) (437226) (INT) [LS] [578700 - 34790921-000] [OP] | 2025-12-08 | 34790921-000 | Purchase Order | No | 0 | 2734.14 | 2734.14
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-07 | 1025902 - Canyon View0352 - 24004 Camino Oceano 24004 Camino Oceano | 0352/ | 4 | C | L | 2026-03-18 | Painting - Exterior / Prep & Enamel (437248) (INT) [LS] [578700 - 34772102-000] [OP] | 2025-12-08 | 34772102-000 | Purchase Order | No | 0 | 1128.44 | 1128.44
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-07 | 1025902 - Canyon View0352 - 24004 Camino Oceano 24004 Camino Oceano | 0352/ | 4 | C | L | 2026-03-23 | Painting - Exterior (437220) (EXT) [578700 - 34733082-000] [UA] | 2025-12-08 | 34733082-000 | EPO | Yes | 0 | 861.64 | 861.64
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-07 | 1025902 - Canyon View0352 - 24004 Camino Oceano 24004 Camino Oceano | 0352/ | 4 | C | L | 2026-03-28 | Painting - Exterior / Prep & Enamel (437232) (INT) [LS] [578700 - 34700150-000] [OP] | 2025-12-08 | 34700150-000 | Purchase Order | No | 0 | 3301.81 | 3301.81
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-10 | 1025903 - Canyon View0353 - 24006 Camino Oceano 24006 Camino Oceano | 0353/ | 5 | D | L | 2026-03-11 | Painting - Interior / Prep & Enamel (437233) (INT) [LS] [578700 - 34747419-000] [OP] | 2025-12-11 | 34747419-000 | Purchase Order | No | 0 | 3179.22 | 3179.22
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-10 | 1025903 - Canyon View0353 - 24006 Camino Oceano 24006 Camino Oceano | 0353/ | 5 | D | L | 2026-03-16 | Painting - Touch Up (437240) (INT) [LS] [578700 - 34757939-000] [OP] | 2025-12-11 | 34757939-000 | Purchase Order | No | 0 | 3659.97 | 3659.97
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-10 | 1025903 - Canyon View0353 - 24006 Camino Oceano 24006 Camino Oceano | 0353/ | 5 | D | L | 2026-03-21 | Painting - Interior / Prep & Enamel (437217) (INT) [LS] [578700 - 34771987-000] [OP] | 2025-12-11 | 34771987-000 | Purchase Order | No | 0 | 1458.55 | 1458.55
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-13 | 1025904 - Canyon View0354 - 24008 Camino Oceano 24008 Camino Oceano | 0354/ | 3 | D | UNKWN | 2026-03-14 | Painting - Exterior (437201) (EXT) [578700 - 34782578-000] [UA] | 2025-12-14 | 34782578-000 | EPO | Yes | 0 | 1004.44 | 1004.44
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-13 | 1025904 - Canyon View0354 - 24008 Camino Oceano 24008 Camino Oceano | 0354/ | 3 | D | UNKWN | 2026-03-19 | Painting - Interior / Prep & Enamel (437245) (INT) [LS] [578700 - 34720758-000] [OP] | 2025-12-14 | 34720758-000 | Purchase Order | No | 0 | 2087.63 | 2087.63
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-13 | 1025904 - Canyon View0354 - 24008 Camino Oceano 24008 Camino Oceano | 0354/ | 3 | D | UNKWN | 2026-03-24 | Painting - Exterior (437235) (EXT) [LS] [578700 - 34753476-000] [OP] | 2025-12-14 | 34753476-000 | Purchase Order | No | 0 | 1326.23 | 1326.23
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-13 | 1025904 - Canyon View0354 - 24008 Camino Oceano 24008 Camino Oceano | 0354/ | 3 | D | UNKWN | 2026-03-29 | Painting - Exterior (437229) (EXT) [578700 - 34715396-000] [UA] | 2025-12-14 | 34715396-000 | EPO | Yes | 0 | 1023.85 | 1023.85
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-13 | 1025904 - Canyon View0354 - 24008 Camino Oceano 24008 Camino Oceano | 0354/ | 3 | D | UNKWN | 2026-04-03 | Painting - Exterior Prime/Fascia (437231) (EXT) [LS] [578700 - 34793926-000] [OP] | 2025-12-14 | 34793926-000 | Purchase Order | No | 0 | 2021.52 | 2021.52
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-13 | 1025904 - Canyon View0354 - 24008 Camino Oceano 24008 Camino Oceano | 0354/ | 3 | D | UNKWN | 2026-04-08 | Painting - Kitchen, Bath & Lids (INT) [LS] | 2025-12-14 |  | Memo | No | 0 | 0 | 0
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-16 | 1025905 - Canyon View0355 - 24010 Camino Oceano 24010 Camino Oceano | 0355/ | 4 | B | L | 2026-03-17 | Painting - Exterior / Prep & Enamel (437212) (INT) [LS] [578700 - 34778561-000] [OP] | 2025-12-17 | 34778561-000 | Purchase Order | No | 0 | 2778.84 | 2778.84
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-16 | 1025905 - Canyon View0355 - 24010 Camino Oceano 24010 Camino Oceano | 0355/ | 4 | B | L | 2026-03-22 | Painting - Exterior Prime/Fascia (437204) (EXT) [LS] [578700 - 34736208-000] [OP] | 2025-12-17 | 34736208-000 | Purchase Order | No | 0 | 3704.36 | 3704.36
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-16 | 1025905 - Canyon View0355 - 24010 Camino Oceano 24010 Camino Oceano | 0355/ | 4 | B | L | 2026-03-27 | Painting - Exterior / Prep & Enamel (437221) (INT) [LS] [578700 - 34766550-000] [OP] | 2025-12-17 | 34766550-000 | Purchase Order | No | 0 | 1935.1 | 1935.1
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-16 | 1025905 - Canyon View0355 - 24010 Camino Oceano 24010 Camino Oceano | 0355/ | 4 | B | L | 2026-04-01 | Painting - Exterior (437218) (EXT) [LS] [578700 - 34795164-000] [OP] | 2025-12-17 | 34795164-000 | Purchase Order | No | 0 | 2044.95 | 2044.95
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-19 | 1025906 - Canyon View0356 - 24012 Camino Oceano 24012 Camino Oceano | 0356/ | 5 | D | R | 2026-03-20 | Painting - Touch Up (437222) (INT) [LS] [578700 - 34743573-000] [OP] | 2025-12-20 | 34743573-000 | Purchase Order | No | 0 | 2931.71 | 2931.71
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-19 | 1025906 - Canyon View0356 - 24012 Camino Oceano 24012 Camino Oceano | 0356/ | 5 | D | R | 2026-03-25 | Painting - Exterior / Prep & Enamel (437229) (INT) [LS] [578700 - 34742176-000] [OP] | 2025-12-20 | 34742176-000 | Purchase Order | No | 0 | 4043.61 | 4043.61
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-19 | 1025906 - Canyon View0356 - 24012 Camino Oceano 24012 Camino Oceano | 0356/ | 5 | D | R | 2026-03-30 | Painting - Interior / Prep & Enamel (437236) (INT) [LS] [578700 - 34750196-000] [OP] | 2025-12-20 | 34750196-000 | Purchase Order | No | 0 | 1817.47 | 1817.47
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-19 | 1025906 - Canyon View0356 - 24012 Camino Oceano 24012 Camino Oceano | 0356/ | 5 | D | R | 2026-04-04 | Painting - Exterior / Prep & Enamel (437202) (INT) [LS] [578700 - 34741704-000] [OP] | 2025-12-20 | 34741704-000 | Purchase Order | No | 0 | 3606.47 | 3606.47
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-19 | 1025906 - Canyon View0356 - 24012 Camino Oceano 24012 Camino Oceano | 0356/ | 5 | D | R | 2026-04-09 | Painting - Exterior / Prep & Enamel (437224) (INT) [LS] [578700 - 34786991-000] [OP] | 2025-12-20 | 34786991-000 | Purchase Order | No | 0 | 3773.38 | 3773.38
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-19 | 1025906 - Canyon View0356 - 24012 Camino Oceano 24012 Camino Oceano | 0356/ | 5 | D | R | 2026-04-14 | Painting - Exterior Prime/Fascia (437231) (EXT) [LS] [578700 - 34704852-000] [OP] | 2025-12-20 | 34704852-000 | Purchase Order | No | 0 | 1441.86 | 1441.86
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-22 | 1025907 - Canyon View0357 - 24014 Camino Oceano 24014 Camino Oceano | 0357/ | 5 | C | R | 2026-03-23 | Painting - Exterior (437233) (EXT) [578700 - 34759890-000] [UA] | 2025-12-23 | 34759890-000 | EPO | Yes | 0 | 707.67 | 707.67
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-22 | 1025907 - Canyon View0357 - 24014 Camino Oceano 24014 Camino Oceano | 0357/ | 5 | C | R | 2026-03-28 | Painting - Exterior Prime/Fascia (437226) (EXT) [LS] [578700 - 34785823-000] [OP] | 2025-12-23 | 34785823-000 | Purchase Order | No | 0 | 4394.85 | 4394.85
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-22 | 1025907 - Canyon View0357 - 24014 Camino Oceano 24014 Camino Oceano | 0357/ | 5 | C | R | 2026-04-02 | Painting - Exterior (437230) (EXT) [578700 - 34734737-000] [UA] | 2025-12-23 | 34734737-000 | EPO | Yes | 0 | 869.28 | 869.28
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-22 | 1025907 - Canyon View0357 - 24014 Camino Oceano 24014 Camino Oceano | 0357/ | 5 | C | R | 2026-04-07 | Painting - Exterior / Prep & Enamel (437241) (INT) [LS] [578700 - 34710527-000] [OP] | 2025-12-23 | 34710527-000 | Purchase Order | No | 0 | 3981.18 | 3981.18
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-22 | 1025907 - Canyon View0357 - 24014 Camino Oceano 24014 Camino Oceano | 0357/ | 5 | C | R | 2026-04-12 | Painting - Exterior / Prep & Enamel (437220) (INT) [LS] [578700 - 34782155-000] [OP] | 2025-12-23 | 34782155-000 | Purchase Order | No | 0 | 3515.51 | 3515.51
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-22 | 1025907 - Canyon View0357 - 24014 Camino Oceano 24014 Camino Oceano | 0357/ | 5 | C | R | 2026-04-17 | Painting - Touch Up (437234) (INT) [LS] [578700 - 34704705-000] [OP] | 2025-12-23 | 34704705-000 | Purchase Order | No | 0 | 3161.11 | 3161.11
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-25 | 1025908 - Canyon View0358 - 24016 Camino Oceano 24016 Camino Oceano | 0358/ | 2 | C | R | 2026-03-26 | Painting - Exterior / Prep & Enamel (437206) (INT) [LS] [578700 - 34799663-000] [OP] | 2025-12-26 | 34799663-000 | Purchase Order | No | 0 | 3218.12 | 3218.12
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-25 | 1025908 - Canyon View0358 - 24016 Camino Oceano 24016 Camino Oceano | 0358/ | 2 | C | R | 2026-03-31 | Painting - Exterior (437228) (EXT) [578700 - 34721805-000] [UA] | 2025-12-26 | 34721805-000 | EPO | Yes | 0 | 1047 | 1047
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-25 | 1025908 - Canyon View0358 - 24016 Camino Oceano 24016 Camino Oceano | 0358/ | 2 | C | R | 2026-04-05 | Painting - Exterior (437202) (EXT) [LS] [578700 - 34742516-000] [OP] | 2025-12-26 | 34742516-000 | Purchase Order | No | 0 | 3786.5 | 3786.5
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-28 | 1025909 - Canyon View0359 - 24018 Camino Oceano 24018 Camino Oceano | 0359/ | 3 | C | L | 2026-03-29 | Painting - Exterior Prime/Fascia (437215) (EXT) [LS] [578700 - 34769621-000] [OP] | 2025-12-29 | 34769621-000 | Purchase Order | No | 0 | 2442.18 | 2442.18
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-28 | 1025909 - Canyon View0359 - 24018 Camino Oceano 24018 Camino Oceano | 0359/ | 3 | C | L | 2026-04-03 | Painting - Exterior Prime/Fascia (437210) (EXT) [LS] [578700 - 34722946-000] [OP] | 2025-12-29 | 34722946-000 | Purchase Order | No | 0 | 1276.39 | 1276.39
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-28 | 1025909 - Canyon View0359 - 24018 Camino Oceano 24018 Camino Oceano | 0359/ | 3 | C | L | 2026-04-08 | Painting - Exterior / Prep & Enamel (437239) (INT) [LS] [578700 - 34789539-000] [OP] | 2025-12-29 | 34789539-000 | Purchase Order | No | 0 | 1842.9 | 1842.9
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-28 | 1025909 - Canyon View0359 - 24018 Camino Oceano 24018 Camino Oceano | 0359/ | 3 | C | L | 2026-04-13 | Painting - Exterior Prime/Fascia (437214) (EXT) [LS] [578700 - 34760443-000] [OP] | 2025-12-29 | 34760443-000 | Purchase Order | No | 0 | 3232.67 | 3232.67
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-28 | 1025909 - Canyon View0359 - 24018 Camino Oceano 24018 Camino Oceano | 0359/ | 3 | C | L | 2026-04-18 | Painting - Touch Up (437216) (INT) [LS] [578700 - 34787404-000] [OP] | 2025-12-29 | 34787404-000 | Purchase Order | No | 0 | 1032.89 | 1032.89
Lennar Corporation - Lennar Orange County | OCH - Canyon View - 5567890 | PRODUCTION/WARRANTY | PH09 - HS 0150-0175 (APR) | 2026-01-28 | 1025909 - Canyon View0359 - 24018 Camino Oceano 24018 Camino Oceano | 0359/ | 3 | C | L | 2026-04-23 | Painting - Touch Up (437218) (INT) [LS] [578700 - 34788815-000] [OP] | 2025-12-29 | 34788815-000 | Purchase Order | No | 0 | 2913.09 | 2913.09